## Pivot
Project Implementation Plan | Sum of No. Days
1. Handshake and Collaboration Setup
1.1. Project Purpose freezing | 2
1.2. Team Formation | 5
1.3. Slack Collaboration Channel setup | 1
1.4. Trello Board for Task management | 6
1.5. Integration of Slack and Trello Collaboration Platform | 7
1.6. MS One Drive and Google Drive setup | 2
1.7. Finalizing Advisor and Advisor Acceptance | 5
1.8. Idea Finalization | 15
2. Project Kick-off
2.1. Literature Research | 37
2.2. Problem Identification | 20
2.3. Project Scoping | 11
2.4. Abstract Draft | 4
2.5. Abstract Submission | 1
2.6. Project Group Start-up Presentation | 1
3. POC (Proof of concept) and Project prototyping
3.1. Data Preparation for Logo validation | 4
3.1.1. Identify target brand label | 30
3.1.2. Manually annotate using Hyperlabel | 15
3.2. Creating a Demo validation Model for dataset | 20
3.2.1. Create a model based on YOLO | 21
3.2.2. Train model based on sample dataset to validate approach | 17
3.3. Validate and increase scope of Data Validation | 22
3.4. Select and Freeze the state-of-art-model for Logo validation | 22
3.5. identify and select the state-of-art-model for URL validation | 22
3.6. Select and Freeze the state-of-the-art model for URL Validation | 22
3.7. Build and Test the ensemble model | 22
3.8. Freeze the ensemble model approach and develop for scaling | 22
4. Train and Build the DL Model
4.1. Freeze and Store the Dataset in standard structured manner | 15
4.2. Create and develop the DL model for Logo Validation | 15
4.3. Create and Develop the DL model for URL Validation | 15
4.4. Create a Deep ensemble model | 10
4.5. Train and Save ensemble model weight | 1
4.6. Finetune the ensemble model | 11
5. Develop the packaged application | 30
6. Testing the packaged application | 30
7. Deploy the packaged application | 30
8. Benchmark and publish performance review | 35
9. Project Closure and Handover | 30
(blank)
Grand Total | 578

## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | AI User Safety Application | [5 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | San Jose State University | [5 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. | GMV Project Team |  | Project Start Date: |  | 2020-07-09
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. |  |  | Scrolling Increment: |  | 1 |  | FALSE | [6 empty] | July | [20 empty] | August
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2020-07-10 to 2020-09-03
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Threat Category | Assigned To | Progress | Start | No. Days | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | 1. Handshake and Collaboration Setup |  |  |  | 2020-07-10
| 1.1. Project Purpose freezing | Goal | Team | 100% | 2020-08-09 | 2 | S: 2; M: 2
| 1.2. Team Formation | Milestone | Gulnara Timokhina | 100% | 2020-07-10 | 5 | bar: F to T
| 1.3. Slack Collaboration Channel setup | Low Risk | Varun Bhaseen | 100% | 2020-08-29 | 1
| 1.4. Trello Board for Task management | Med Risk | Varun Bhaseen | 100% | 2020-08-06 | 6
| 1.5. Integration of Slack and Trello Collaboration Platform | On Track | Varun Bhaseen | 100% | 2020-08-29 | 7
| 1.6. MS One Drive and Google Drive setup | Low Risk | Mirsaeid Abolghasemi | 100% | 2020-08-12 | 2
| 1.7. Finalizing Advisor and Advisor Acceptance | Goal | Team | 100% | 2020-07-13 | 5 | M: 2; T: 2; W: 2; T: 2; F: 2
| 1.8. Idea Finalization | High Risk | Team | 100% | 2020-07-18 | 15
| 2. Project Kick-off |  |  |  | 2020-08-11
| 2.1. Literature Research | On Track | Mirsaeid Abolghasemi | 100% | 2020-08-15 | 37
| 2.2. Problem Identification | High Risk | Gulnara Timokhina | 100% | 2020-08-11 | 20
| 2.3. Project Scoping | Low Risk | Varun Bhaseen | 100% | 2020-08-30 | 11
| 2.4. Abstract Draft | Goal | Team | 100% | 2020-08-30 | 4 | S: 2; M: 2; T: 2; W: 2
| 2.5. Abstract Submission | Milestone | Team | 100% | 2020-09-03 | 1 | bar: T
| 2.6. Project Group Start-up Presentation | Milestone | Team | 100% | 2020-09-07 | 1
| 3. POC (Proof of concept) and Project prototyping |  |  |  | 2020-08-24
| 3.1. Data Preparation for Logo validation | Milestone | Gulnara Timokhina | 100% | 2020-08-24 | 4 | bar: M to T
| 3.1.1. Identify target brand label | On Track | Gulnara Timokhina | 100% | 2020-08-27 | 30
| 3.1.2. Manually annotate using Hyperlabel | High Risk | Gulnara Timokhina | 100% | 2020-09-11 | 15
| 3.2. Creating a Demo validation Model for dataset | On Track | Varun Bhaseen | 100% | 2020-09-07 | 20
| 3.2.1. Create a model based on YOLO | Low Risk | Varun Bhaseen | 100% | 2020-09-09 | 21
| 3.2.2. Train model based on sample dataset to validate approach | Med Risk | Varun Bhaseen | 100% | 2020-09-09 | 17
| 3.3. Validate and increase scope of Data Validation | High Risk | Mirsaeid Abolghasemi | 100% | 2020-09-09 | 22
| 3.4. Select and Freeze the state-of-art-model for Logo validation | Low Risk | Team | 100% | 2020-09-09 | 22
| 3.5. identify and select the state-of-art-model for URL validation | On Track | Mirsaeid Abolghasemi | 100% | 2020-09-21 | 22
| 3.6. Select and Freeze the state-of-the-art model for URL Validation | Low Risk | Mirsaeid Abolghasemi | 100% | 2020-09-21 | 22
| 3.7. Build and Test the ensemble model | High Risk | Varun Bhaseen | 100% | 2020-09-21 | 22
| 3.8. Freeze the ensemble model approach and develop for scaling | Milestone | Varun Bhaseen | 100% | 2020-09-25 | 22
| 4. Train and Build the DL Model |  |  |  | 2020-10-17
| 4.1. Freeze and Store the Dataset in standard structured manner | High Risk | Gulnara Timokhina | 100% | 2020-10-17 | 15
| 4.2. Create and develop the DL model for Logo Validation | On Track | Varun Bhaseen | 100% | 2020-10-27 | 15
| 4.3. Create and Develop the DL model for URL Validation | Med Risk | Mirsaeid Abolghasemi | 100% | 2020-10-27 | 15
| 4.4. Create a Deep ensemble model | Low Risk | Gulnara Timokhina | 100% | 2020-11-11 | 10
| 4.6. Finetune the ensemble model | Low Risk | Varun Bhaseen | 100% | 2020-11-12 | 11
| 4.5. Train and Save ensemble model weight | High Risk | Mirsaeid Abolghasemi | 100% | 2020-11-25 | 1
This is an empty row | 5. Develop the packaged application | High Risk | Team | 100% | 2020-12-22 | 30
| 6. Testing the packaged application | High Risk | Team | 100% | 2021-01-04 | 30
| 7. Deploy the packaged application | Med Risk | Team | 100% | 2021-01-31 | 30
| 8. Benchmark and publish performance review | Low Risk | Team | 100% | 2021-02-13 | 35
| 9. Project Closure and Handover | Low Risk | Team | 100% | 2021-03-12 | 30
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one.
To add more data, Insert new rows ABOVE this one