## Project Timeline
PROJECT TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE | Position Adjusted | Date adjusted | Milestone adjusted
2020-07-10 | Project Start: | 25 | 0 | 25 | 2020-07-10 | Project Start:
2020-09-04 | Milestone 1: Handshake and Collaboration Setup | 10 | 0 | 10 | 2020-09-04 | Milestone 1: Handshake and Collaboration Setup
2020-09-20 | Milestone 2: Project Kick-off | -10 | 0 | -10 | 2020-09-20 | Milestone 2: Project Kick-off
2020-10-11 | Milestone 3: POC (Proof of concept) and Project prototyping | 20 | 0 | 20 | 2020-10-11 | Milestone 3: POC (Proof of concept) and Project prototyping
2020-11-25 | Milestone 4: Train and Build the DL Model | -15 | 0 | -15 | 2020-11-25 | Milestone 4: Train and Build the DL Model
2021-01-20 | Milestone 5: Develop the packaged application | 15 | 0 | 15 | 2021-01-20 | Milestone 5: Develop the packaged application
2021-02-02 | Milestone 6: Testing the packaged application | -8 | 0 | -8 | 2021-02-02 | Milestone 6: Testing the packaged application
2021-03-01 | Milestone 7: Deploy the packaged application | 8 | 0 | 8 | 2021-03-01 | Milestone 7: Deploy the packaged application
2021-03-19 | Milestone 8: Benchmark and publish performance review | -20 | 0 | -20 | 2021-03-19 | Milestone 8: Benchmark and publish performance review
2021-04-09 | Milestone 9: Project Closure and Handover | 20 | 0 | 20 | 2021-04-09 | Milestone 9: Project Closure and Handover
2021-05-18 | Project End | -15 | 0 | 5 | #NAME?

## Project Data Sorted (hidden)
Sort the dates to populate the timeline in chronological order
|  |  | data analysis | [5 empty] | Actual data to chart, which is fed into the Project Timeline worksheet via hidden columns F-H.
| start row | 5 | TIE BREAK | RANK | DATE | MILESTONE | POSITION | NUM | RANK Sorted | DATE | MILESTONE | POSITION
| last entry | 15 | 11 | 1 | 2020-07-10 | Project Start: | 25 | 10 | 11 | 2020-07-10 | Project Start: | 25
|  |  | 10 | 2 | 2020-09-04 | Milestone 1: Handshake and Collaboration Setup | 10 | 9 | 10 | 2020-09-04 | Milestone 1: Handshake and Collaboration Setup | 10
|  |  | 9 | 3 | 2020-09-20 | Milestone 2: Project Kick-off | -10 | 8 | 9 | 2020-09-20 | Milestone 2: Project Kick-off | -10
|  |  | 8 | 4 | 2020-10-11 | Milestone 3: POC (Proof of concept) and Project prototyping | 20 | 7 | 8 | 2020-10-11 | Milestone 3: POC (Proof of concept) and Project prototyping | 20
|  |  | 7 | 5 | 2020-11-25 | Milestone 4: Train and Build the DL Model | -15 | 6 | 7 | 2020-11-25 | Milestone 4: Train and Build the DL Model | -15
|  |  | 6 | 6 | 2021-01-20 | Milestone 5: Develop the packaged application | 15 | 5 | 6 | 2021-01-20 | Milestone 5: Develop the packaged application | 15
|  |  | 5 | 7 | 2021-02-02 | Milestone 6: Testing the packaged application | -8 | 4 | 5 | 2021-02-02 | Milestone 6: Testing the packaged application | -8
|  |  | 4 | 8 | 2021-03-01 | Milestone 7: Deploy the packaged application | 8 | 3 | 4 | 2021-03-01 | Milestone 7: Deploy the packaged application | 8
|  |  | 3 | 9 | 2021-03-19 | Milestone 8: Benchmark and publish performance review | -20 | 2 | 3 | 2021-03-19 | Milestone 8: Benchmark and publish performance review | -20
|  |  | 2 | 10 | 2021-04-09 | Milestone 9: Project Closure and Handover | 20 | 1 | 2 | 2021-04-09 | Milestone 9: Project Closure and Handover | 20
|  |  | 1 | 11 | 2021-05-18 | Project End | -15 | 0 | 1 | 2021-05-18 | Project End | -15